## Sheet1
Related User Story | Task Description | Initial Estimate | Amount Remaining After…
View available law school listings | Create a LawSchool class to hold listing information | 2 | 11 | 8 | 5 | 2
View available law school listings | Add sample law school listings | 1.5
View available law school listings | Build the main window showing the list of schools | 2
View a law school’s application details | Build a second window showing the selected school’s details | 2
View a law school’s application details | Make selecting/clicking a school open the details window | 1.5
Open the official application link | Add a button to open the school’s official application link | 1.5
Adding a new listing | Build the UI for adding a new law school listing | 2
Search listings | Add search/filter behavior to the school listing page | 2
Estimate Totals |  | 14.5 | 11 | 8 | 5 | 2